## Definition of Milestones（2023） (hidden)
New Gsite Roadmap 2023
Release Ver. | Planned Release Schedule |  | Version Definition
| according to 2 team's productivity | according to 3 team's productivity | Goal and value | Product strategy | Main features
Release v0.3 | 2023/5/22(Completed at the end of No.2 Sprint) | 2023/5/22(Completed at the end of No.2 Sprint) | 1. To provide more effective model interaction and presentation which improves user experience when navigating the models | Strategy 1：Design management and collaboration improvement based on upgraded drawing and BIM model capability | 1、BIM model management per UK ISO 19650 (Completed) 2、Model Integration 3、Location setting 4、Automatic room recognition 5、Location import from BIM model （Detail: Plan draft for 2 teams）
2. Easy accessibility for the most current drawings and BIM models,for all stakeholders anytime and anywhere
3. Drawing recognition and extraction to achieve easy-to-use upload/publish/manage drawing processes
Release v0.5 | 2023/7/3(Completed at the end of No.6 Sprint) | 2023/6/5(Completed at the end of No.4 Sprint) | 1. To enhance the ability to associate BIM model and drawings with collaboration items such as quality/safety issues, RFIs, etc., making design documents the central hub for information integration with visual assistance and clear tracking orientation |  | 1、Drawing OCR and Extraction (Completed) 2、Drawing management per UK ISO 19650 (Completed) 3、Drawing linkage with RFIs (Completed) 4、2D-3D interconnection 5、2D-3D Linkage with Issues 6、Automatic drawing hyperlinks 7、2D-4D Linkage with RFIs （Detail: Plan draft for 2 teams）
2.Optimize current functions to improve the problem solving for client’s pain points in actual business scenarios
Release v1.0 | 2023/9/11(Completed at the end of No.10 Sprint) | 2023/7/31(Completed at the end of No.7 Sprint) | 1.Improve the coordination efficiency among stakeholders on the construction site, timely deal with issues, and track items with various statues | Strategy 3: Optimize on-site collaboration management functions | 1、Site Diary 2、Drawing markup upgrades 3、RFI Various attachment choices 4、RFI mobile 5、Specification Automatic chapter recognition and extraction 6、Specification revision management 7、Specification linkage with other items 8、Instant Message - Voice call 9、Instant Message - Video call （Detail: Plan draft for 2 teams）
2.Linkage between collaboration items and drawing-model to provide clear visualization and orientation
Release v1.5 | 2023/10/16(Completed at the end of No.12 Sprint) | 2023/8/14(Completed at the end of No.8 Sprint) | 1.Implement the localized design of Dashboard to achieve friendly user experience | Strategy 2: Implement Dashboard optimization for management level | 1、Project dashboard 2、Project quality problem statistical analysis 3、Project safety problem statistical analysis 4、Project progress analysis （Detail: Plan draft for 2 teams）
2.Data organization can be customized according to different access levels with corresponding data analysis to provide insights
3.Provide linkage between statistics and individual issue details so that everything is traceable
Release V2.0 | 2023/12/25(Completed at the end of No.17 Sprint) | 2023/10/16(Completed at the end of No.12 Sprint) | 1.Optimize current functions to improve the problem solving for client’s pain points in actual business scenarios | Strategy 4: Improve and optimize the original Field, Progress and Track Strategy 6: Provide highlights with promotional features | 1、Checklists 2、Documents 3、AI （Detail: Plan draft for 2 teams）
2.Design new function points, open up business linkages between business aspects, and increase the range of business functions
3. To comply with the UK local management standards and local document management regulations
4. Enhance the publicity attraction which can be developed in future version if needed

## 2024 Milestones (hidden)
Gsite Product Strategy 2024 (first half)
Strategy 1
Content | Description
Subject | Gsite-Asite Integration Phase 1
Goal & Value | 1. Provide user single sign-on so that Asite users can automatically log on Gsite
2. Allow easy setup for user with Asite priviledge
3. Seamless Data transmission between 2 systems
Features | 1. User single sign-on
2. File, exports, and data transmission between Gsite and Asite
3. Access control single setup
4. CDE+Gsite value function flow
Priority | High
Strategy 2
Content | Description
Subject | Gsite Tablet First Version
Goal & Value | 1. Provide a Gsite tablet App to cover field related modules
2. Online/Offline mode to cover all site scenarios
Features | 1. Tablet Issue management
2. Tablet Gsite Album
3. Tablet Drawings
4. Tablet 2D-3D enabled field applications
5. Online/Offline synchronisation
Priority | High
Strategy 3
Content | Description
Subject | Existing Module Value Upgrade
Goal & Value | 1. Improve the coordination efficiency among stakeholders on the construction site, timely deal with issues, and track items with various statues
2. Improve existing module with easy-to-use features
3. Enterprise-level data import and export for users to reuse templates
Features | 1. More flexible Access Control functions
2. PDF OCR optimisation and hyperlinks
3. Submittal Multi-party online collaborative markups
4. 3D viewpoint label and markup optimisations
5. Forms workflow enhancement
6. Enterprise-level templates import and export
7. PDF & Model performance improvement
8. Notification function optimisations
9. Component Unifications (Filter, Archive, Reference, etc.)
10. Part L Album updates
11. Instant Message improved collaborative functions
Priority | High
Strategy 4
Content | Description
Subject | Implement Dashboard optimization for management level
Goal & Value | 1.Implement the localized design of Dashboard to achieve friendly user experience
2.Data organization can be customized according to different access levels with corresponding data analysis to provide insights
3.Provide linkage between statistics and individual task details so that everything is traceable
4.Support data integration with third party analytic tools, to provide more customizability and better transition.
Features | 1.Issue Dashboard
2.Inspection Completion Dashboard
3.Site Diary Log Board
4.RFI Dashboard
5.Submittal Dashboard
6.Task Board (To-do)
7.Project/Personal Dashboard
8.Enterprise Level Dashboard (Later Stage)
9.Customizable Layout
10. Chat message Entry
11. Thrid Party Tool Entry Access
Priority | High

## 6月迭代日历 (hidden)
2025 | 六月 |  | 星期一
45068 | 45069 | 45070 | 45071 | 45072 | 45073 | 45074
2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04
| 迭代计划会 D1 | D2 | D3 | D4
2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11
D5 | D6 概设完成（评审通过） | D7 | D8 | D9 详设完成（评审通过）
2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18
D10 预交底Backlog 迭代演示会 | 间歇 详细需求交底 子任务拆分 迭代总结会 | 迭代计划会 D1 | D2 | D3
2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25
D4 概设完成（评审通过） | D5 | D6 | 端午节假期 | 端午节假期 | 端午节假期 | 补班 D7
2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02
D8 详设完成（评审通过） | D9 预交底Backlog 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1 | D2
#NAME?
D2 | D3 | D4 | D5 | D6
Sprint06
Sprint07
Sprint08

## 7月迭代日历 (hidden)
2025 | 七月 |  | 星期一
45096 | 45097 | 45098 | 45099 | 45100 | 45101 | 45102
2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02
D8 详设完成（评审通过） | D9 预交底Backlog 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1 | D2
2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09
D3 | D4 概设完成（评审通过） | D5 | D6 | D7
2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16
D8 详设完成（评审通过） | D9 预交底Backlog 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1 | D2
2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23
D3 | D4 | D5 概设完成（评审通过） | D6 | D7 系统测试
2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30
D8 系统测试 | D9 系统测试 | D10 详设完成（评审通过） 系统测试 | D11 系统测试 | D12 系统测试
2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06
迭代计划会 D1 | D2 | D3 系统测试 | D5 系统测试 | D6 系统测试
Sprint08
Sprint08
Sprint09
Sprint10

## 8月迭代日历 (hidden)
2025 | 八月 |  | 星期一
45131 | 45132 | 45133 | 45134 | 45135 | 45136 | 45137
2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06
迭代计划会 D1 | D2 | D3 UAT系统测试 | D5 UAT系统测试 | D6 UAT系统测试 发版评审
2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13
D7 UK上线 UK系统测试 | D8 UK系统测试 | D8 UK上线 UK系统测试 | D8 UK系统测试 UK发版完成 | 迭代计划会 D1
2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20
D2 | D3 概设完成（评审通过） | D4 | D5 | D6
2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27
D7 | D8 | D9 预交底Backlog 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1
2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03
D2 | D3 概设完成（评审通过） | D4 | D5 | D6
#NAME?
Sprint10
Sprint11
Sprint12

## 2024年1月 (hidden)
2024 | 一月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06
元旦假期 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1 | D2 | D3
1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13
D4 初审共识 | D5 | D6 | D7 详设完成（评审通过） | D8
1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20
D9 预交底Backlog 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1 | D2 | D3
1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27
D4 初审共识 | D5 | D6 产品走查 | D7 详设完成（评审通过） 产品走查 | D8 预交底Backlog 产品走查
1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03
D9 详细需求交底 产品走查 | D10 产品走查 迭代演示会 子任务拆分 | 集成测试 D1 | D2 集成测试 | D3 初审共识 集成测试 |  | 补班 D4 系统测试(UK-Pre)
1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10
D5 系统测试(UK-Pre) | D6 系统测试(UK-Pre) | 公司统一年假 | 公司统一年假 | 公司统一年假 | 2024春节假期 | 春节假期

## 2024年2月 (hidden)
2024 | 二月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03
D9 详细需求交底 产品走查 | D10 产品走查 迭代演示会 子任务拆分 | 集成测试 D1 | D2 集成测试 | D3 初审共识 集成测试 |  | 补班 D4 系统测试(UK-Pre)
1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10
D5 系统测试(UK-Pre) | D6 系统测试(UK-Pre) | 公司统一年假 传卜，舒昕 皑欣 恭豪 | 公司统一年假 永涛，志慧 四雯 恭豪 | 公司统一年假 鱼宁 李根； 杨雪 恭豪 | 2024春节假期 传卜，舒昕 杨雪 恭豪 | 春节假期 邹斌，庆瑞 皑欣 恭豪 | -
1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17
春节假期 伟伟，荣枫 四雯 恭豪 | 春节假期 传卜，舒昕 胜宇 恭豪 | 春节假期 牛鸽，志慧 胜宇 恭豪 | 春节假期 德翔，庆忠 胜宇 恭豪 | 春节假期 传卜，舒昕 胜宇 恭豪 | 春节假期 牛鸽，庆瑞 胜宇 恭豪 | 补班 D7
1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24
D8 UK上线测试 详设完成（评审通过） | D9 UK上线测试 | D10 预交底Backlog 详细需求交底 | D11 迭代演示会 子任务拆分 | 迭代间歇 迭代总结会
1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1899-12-31 | 1900-01-01 | 1900-01-02
迭代计划会 D1 | D2 | D3 | D4 初审共识 | D5

## 2024年3月 (hidden)
2025 | 三月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1899-12-31 | 1900-01-01 | 1900-01-02
迭代计划会 D1 | D2 | D3 | D4 初审共识 | D5
1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09
D6 | D7 详设完成（评审通过） | D8 预交底Backlog | D9 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会
1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16
迭代计划会 D1 | D2 | D3 | D4 初审共识 | D5
1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23
D6 | D7 详设完成（评审通过） | D8 预交底Backlog | D9 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会
1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30
迭代计划会 D1 | D2 | D3 | D4 初审共识 | D5
1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06
D6 | D7 详设完成（评审通过） | D8 预交底Backlog | 清明假期 | 清明假期 | 清明假期 | 补班 D9 详细需求交底

## 2024年4月 (hidden)
2025 | 四月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06
D6 | D7 详设完成（评审通过） | D8 预交底Backlog | 清明假期 | 清明假期 | 清明假期 | 补班 D9 详细需求交底
1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13
D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1 | D2 | D3 | D4 初审共识
1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20
D5 | D6 产品走查 | D7 详设完成（评审通过） 产品走查 | D8 产品走查 | D9 产品走查 集成测试
1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27
D10 产品走查 集成测试 | 系统测试(UK-Pre) D1 | D2 系统测试(UK-Pre) | D3 UK上线测试 | D4 UK上线测试 预交底Backlog |  | 补班 D5 详细需求交底
1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04
D6 子任务拆分 | 迭代间歇 迭代总结会 | 劳动节假期 | 劳动节假期 | 劳动节假期 | 劳动节假期 | 劳动节假期

## 2024年5月 (hidden)
2025 | 五月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04
D6 子任务拆分 | 迭代间歇 迭代总结会 | 劳动节假期 | 劳动节假期 | 劳动节假期 | 劳动节假期 | 劳动节假期
1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11
迭代计划会 D1 | D2 | D3 | D4 初审共识 | D5 | 补班 D6
1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18
D7 详设完成（评审通过） | D8 预交底Backlog | D9 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1
1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25
D2 | D3 | D4 初审共识 | D5 | D6
1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01
D7 详设完成（评审通过） | D8 预交底Backlog | D9 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1
1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08
D2 | D3 | D4 初审共识 | D5 | D6 | 端午节假期 | 端午节假期

## 2024年6月 (hidden)
2025 | 六月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01
D7 详设完成（评审通过） | D8 预交底Backlog | D9 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会 | 迭代计划会 D1
1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08
D2 | D3 | D4 初审共识 | D5 | D6 | 端午节假期 | 端午节假期
1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15
端午节假期 | D7 详设完成（评审通过） | D8 预交底Backlog | D9 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会
1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22
迭代计划会 D1 | D2 | D3 | D4 初审共识（停一次） 测试平台统一版本app | D5
1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29
D6 | D7 | D8 预交底Backlog（暂停一次） | D9 详细交底 | D10 迭代演示会 子任务拆分 迭代总结会
1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06
SP33-D1 迭代计划会 平台统一app上架 | D2 | D3 | D4 初审共识 | D5

## 2024年7月 (hidden)
2025 | 七月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06
D1 ukpre 部署 ukpre 产品走查 ukpre 系统测试 ukpre UI 走查 | D2 ukpre 产品走查 ukpre 系统测试 ukpre UI 走查 | D3 ukpre 产品走查 ukpre 系统测试 ukpre UI 走查 | D4 ukpre 产品走查 ukpre 系统测试 ukpre UI 走查 | D5 走查问题收尾
8 | 9 | 10 | 11 | 12 | 13 | 14
D6 uk 部署 uk 测试验证 初审共识 pad 离线模式发布 | D7 UAT 部署 uat 测试 | D8 预交底 Backlog | D9 需求交底 | D10 迭代计划会 总结会
1900-01-14 | 16 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20
D1 迭代计划会 | D2 | D3 | D4 初审共识 | D5
1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27
D6 | D7 | D8 预交底 Backlog | D9 详细需求交底 | D10 迭代演示会 子任务拆分 迭代总结会
1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03
SP35-D1 迭代计划会 | D2 | D3 | D4 初审共识 | D5
1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10
D6 | D7 | D8 预交底Backlog | D9 | D10 迭代演示会 子任务拆分 迭代总结会

## 2024年8月 (hidden)
2025 | 八月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03
SP35-D1 迭代计划会 | D2 | D3 | D4 初审共识 | D5
1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10
D6 | D7 | D8 预交底Backlog | D9 详细交底 | D10 迭代演示会 子任务拆分 迭代总结会
1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17
SP36-D1 迭代计划会 | D2 | D3 | D4 SP37-初审共识 | D5
1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24
D6 | D7 | D8 SP37-预交底Backlog | D9 详细交底 | D10 迭代演示会 子任务拆分 迭代总结会
1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31
SP37-D1 迭代计划会 | D2 | D3 | D4 初审共识 | D5
1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07

## 2024年9月 (hidden)
2025 | 九月 |  | 星期一
45194 | 45195 | 45196 | 45197 | 45198 | 45199 | 45200
2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01
SP37-D1 迭代计划会 | D2 | D3 | D4 初审共识 | D5
2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08
D6 | D7 | D8 1.SP38-预交底Backlog 2. 最终确认发版范围 | D9 详细交底 | D10 迭代演示会 子任务拆分 迭代总结会
2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15
SP38-D1 ( 走查开始日 ) 1.迭代计划会 2.UKPre 部署 3.产品走查 4. UI 走查 5. 系统测试 | D2 1.ukpre 产品走查 2.ukpre UI 走查 3. 走查问题共识 4.开发修复 5. 系统测试 | D3 1.ukpre 产品走查 2.ukpre UI 走查 3. 走查问题共识 4.开发修复 5. 系统测试 | D4（走查截止日） 1.ukpre 产品走查 2.ukpre UI 走查 3. 走查问题共识 4.开发修复 5. 系统测试 SP39-初审共识 | D5 1. ukpre 开发收尾 2. ukpre 走查验收 3. ukpre 测试验证 4. document2.0 技术交底 | D6（上班） 1. ukpre 开发收尾 2. ukpre 走查验收 3. ukpre 测试验证 | 中秋节
2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22
中秋节 | 中秋节 八月十五 | D7 （封版日） 1. ukpre 开发收尾 2. ukpre 走查验收 3. ukpre 测试验证 4. UK 部署准备（代码合并，checklist 确认） | D8 （发版日 9 点-11 点） 1. UK-Gsite 部署上线 2. UK-Gsite 测试验证 3. UK-项管平台-830版本 部署 | D9 1.SP39-预交底Backlog 2. 详细交底 3. 发版观察反馈 4. UAT 合并部署测试验证
2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29
D10 1.子任务拆分 2. 迭代总结会 3. UAT 测试验证 | SP39-D1 迭代计划会 | D2 | D3 | D4 SP40-初审共识 |  | D5（上班）
#NAME?

## 2024年10月 (hidden)
2025 | 十月 |  | 星期一
45194 | 45195 | 45196 | 45197 | 45198 | 45199 | 45200
2024-09-30 | 2024-10-01 | 2 | 3 | 4 | 5 | 6
SP39-D6 李恭豪 周胜宇 王舒昕 | 国庆长假 李恭豪 周胜宇 程中亮 | 国庆长假 李恭豪 周胜宇 吴传卜 | 国庆长假 李恭豪 康四雯 吴传卜 | 国庆长假 李恭豪 康四雯 宋飞飞 | 国庆长假 李恭豪 杨雪 宋飞飞 | 国庆长假 李恭豪 余皑欣 王舒昕
7 | 8 | 9 | 10 | 11 | 12 | 13
国庆长假 李恭豪 余皑欣 程中亮 | SP39-D7 李恭豪 杨雪 吴传卜 | D8 | D9 SP40-预交底Backlog | D10 迭代演示会 子任务拆分 详细交底 | 迭代间歇 - 迭代准备 -迭代总结会 - 迭代缓冲 - Q4 规划沟通
14 | 15 | 16 | 17 | 18 | 19 | 20
SP40-D1 迭代计划会 | D2 | D3 | D4 初审共识 | D5
21 | 22 | 23 | 24 | 25 | 26 | 27
D6 | D7 | D8 预交底Backlog | D9 详细交底 | D10 迭代演示会 子任务拆分 迭代总结会
28 | 29 | 30 | 31 | 2024-11-01 | 2 | 3
SP41-D1 迭代计划会 | D2 | D3 | D4 初审共识
4 | 5 | 6 | 7 | 8 | 9 | 10

## 2024年11月 (hidden)
2025 | 十一月 |  | 星期一
45222 | 45223 | 45224 | 45225 | 45226 | 45227 | 45228
2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03
SP41-D1 迭代计划会 | D2 | D3 | D4 初审共识-SP42 | D5
2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10
D6 | D7 | D8 预交底Backlog-SP42 | D9 详细交底 | D10 迭代演示会 子任务拆分 迭代总结会
2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17
SP42-D1 迭代计划会 | D2 | D3 1. Test环境平台升级1030版本 2. Test环境平台合版验证 | D4 1. Test环境平台合版验证 | D5 初审共识-SP43+SP44 1. 集成平台-自定义首页按租户能够灵活配置发布到测试环境
2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24
D6 需求评审 - SP43-44 | D7 | D8 预交底Backlog -SP43 1. 完成 checklist 准备（权限，菜单，sql，配置项） 2. 收集下个月平台需求并和对方预约沟通时间 | D9 详细交底 -SP43 | D10 1.Gsite UKPre 代码合并&部署 子任务拆分 迭代总结会
2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01
SP43-技术任务+发版迭代-D1 【 手机同源R1& 离线优化v1.2 + 平台升级1030 + Athena版本上线】 迭代计划会 0. 确认部署完毕，通知大家走查 1. UKPre 产品走查 2. UKPre UI走查 数据冲突 & 离线同步处理--业务方案 | D2 1.UKPre产品走查 2.UKPre UI走查 3.UKPre系统测试 4.App提交审核，通过后暂不发布 | D3 1. UKPre 产品走查 2. UKPre UI走查 3. UKPre系统测试 | D4 Gsite马来Soft Launch活动 1. UKPre 产品走查 2. UKPre UI走查 3. UKPre系统测试 | D5 1. UKPre 产品走查 2. UKPre UI走查 3. UKPre系统测试 4. iOS 白牌开发完成（祁栋）
2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08
D6 1. UKPre 产品走查 2. UKPre UI走查 3. UKPre系统测试 | D7 预交底Backlog -SP44 1. UKPre 产品走查（截止） 2. UKPre UI走查（截止） | D8 详细交底-SP44 | D9 子任务拆分 迭代总结会 版本计划月度检视 | D10 1. UK发版(Web) 2. 平台升级验证 3. UK线上验证 4. UK Web上线后App发布新版

## 2026-01
2026 年 1 月
45250 | 45251 | 45252 | 45253 | 45254 | 45255 | 45256
2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04
2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11
2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18
2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25
2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01
2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08

## 2026-02
2026 年 2 月
45250 | 45251 | 45252 | 45253 | 45254 | 45255 | 45256
2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01
2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08
2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15
[5 empty] | 春节（班） | 春节（休）
2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22
春节（休） | 春节（休） | 春节（休） | 春节（休） | 春节（休） | 春节（休） | 春节（休）
2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01
春节（休） |  |  |  |  | 春节（班）
2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08

## 2025-6(副本) (hidden)
2025 | 六月 |  | 星期一
45250 | 45251 | 45252 | 45253 | 45254 | 45255 | 45256
26 | 27 | 28 | 29 | 30 | 31 | 1
D6 | D7 预交底Backlog-SP56 | D8 | D9 | SP55-D10 子任务拆分 迭代总结会 | 端午节假期 | 端午节假期
2 | 3 | 4 | 5 | 6 | 7 | 8
端午节假期 | SP56- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4
9 | 10 | 11 | 12 | 13 | 14 | 15
D5 | D6 | D7 预交底Backlog-SP57 | D8 详细交底-SP57 | D9
16 | 17 | 18 | 19 | 20 | 21 | 22
SP56-D10 子任务拆分 迭代总结会 | SP57- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4
23 | 24 | 25 | 26 | 27 | 28 | 29
D5 | D6 | D7 预交底Backlog-SP58 | D8 详细交底-SP58 | D9
30 | 1 | 2 | 3 | 4 | 5 | 6
SP57-D10 子任务拆分 迭代总结会 | SP58- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4

## 2025-6(副本1) (hidden)
2025 | 六月 |  | 星期一
45250 | 45251 | 45252 | 45253 | 45254 | 45255 | 45256
26 | 27 | 28 | 29 | 30 | 31 | 1
D6 | D7 预交底Backlog-SP56 | D8 | D9 | SP55-D10 子任务拆分 迭代总结会 | 端午节假期 | 端午节假期
2 | 3 | 4 | 5 | 6 | 7 | 8
端午节假期 | SP56- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4
9 | 10 | 11 | 12 | 13 | 14 | 15
D5 | D6 | D7 预交底Backlog-SP57 | D8 详细交底-SP57 | D9
16 | 17 | 18 | 19 | 20 | 21 | 22
SP56-D10 子任务拆分 迭代总结会 | SP57- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4
23 | 24 | 25 | 26 | 27 | 28 | 29
D5 | D6 | D7 预交底Backlog-SP58 | D8 详细交底-SP58 | D9
30 | 1 | 2 | 3 | 4 | 5 | 6
SP57-D10 子任务拆分 迭代总结会 | SP58- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4

## 2025-6(副本2) (hidden)
2025 | 六月 |  | 星期一
45250 | 45251 | 45252 | 45253 | 45254 | 45255 | 45256
26 | 27 | 28 | 29 | 30 | 31 | 1
D6 | D7 预交底Backlog-SP56 | D8 | D9 | SP55-D10 子任务拆分 迭代总结会 | 端午节假期 | 端午节假期
2 | 3 | 4 | 5 | 6 | 7 | 8
端午节假期 | SP56- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4
9 | 10 | 11 | 12 | 13 | 14 | 15
D5 | D6 | D7 预交底Backlog-SP57 | D8 详细交底-SP57 | D9
16 | 17 | 18 | 19 | 20 | 21 | 22
SP56-D10 子任务拆分 迭代总结会 | SP57- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4
23 | 24 | 25 | 26 | 27 | 28 | 29
D5 | D6 | D7 预交底Backlog-SP58 | D8 详细交底-SP58 | D9
30 | 1 | 2 | 3 | 4 | 5 | 6
SP57-D10 子任务拆分 迭代总结会 | SP58- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4

## 2025-6(副本3) (hidden)
2025 | 六月 |  | 星期一
45250 | 45251 | 45252 | 45253 | 45254 | 45255 | 45256
26 | 27 | 28 | 29 | 30 | 31 | 1
D6 | D7 预交底Backlog-SP56 | D8 | D9 | SP55-D10 子任务拆分 迭代总结会 | 端午节假期 | 端午节假期
2 | 3 | 4 | 5 | 6 | 7 | 8
端午节假期 | SP56- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4
9 | 10 | 11 | 12 | 13 | 14 | 15
D5 | D6 | D7 预交底Backlog-SP57 | D8 详细交底-SP57 | D9
16 | 17 | 18 | 19 | 20 | 21 | 22
SP56-D10 子任务拆分 迭代总结会 | SP57- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4
23 | 24 | 25 | 26 | 27 | 28 | 29
D5 | D6 | D7 预交底Backlog-SP58 | D8 详细交底-SP58 | D9
30 | 1 | 2 | 3 | 4 | 5 | 6
SP57-D10 子任务拆分 迭代总结会 | SP58- D1 【迭代目标？】 迭代计划会 | D2 | D3 | D4

## 2024年9月 (2) (hidden)
2025 | 九月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31
1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07
1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14
1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21
1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28
1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05

## 2024年10月 (2) (hidden)
2025 | 十月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19
1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26
1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02
1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09

## 2024年11月 (2) (hidden)
2025 | 十一月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02
1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09
1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16
1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23
1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31
1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07

## 2024年12月 (2) (hidden)
2025 | 十二月 |  | 星期一
星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31
1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07
1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14
1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21
1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28
1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04